|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan 2022-24** | | | | | |
| **Activities** | **Lead**  **Officer/Organisations** | **Expected**  **Milestone/Outcomes** | **Performance**  **Measure** | **CTLP**  **Priorities** | **Completion**  **Of Actions** |
| **1. EFFECTIVE LEADERSHIP** | | | |  |  |
| 1.1 Review CONTEST Governance arrangements and ensure effective linkage to relevant District Partnerships and Strategies. | CONTEST partners | Strengthen CONTEST performance management to ensure effective leadership is provided to partners  Membership and terms of reference are appropriate and effective.  Partnership groups are aligning national policies with local delivery plan.  Effective leadership arrangements that build resilience to the influence of  terrorist narratives in the district. | Full recorded partnership buy-in into delivery groups  Four CONTEST and twelve Channel meetings per year  LA CONTEST meetings 4 times a year to review progress against Prevent Plan | Links to all priorities to have effective governance arrangements and to link in to district partnerships and strategies | All meetings completed by March 2023 and again by March 2024.  Terms of reference reviewed at CONTEST Q4 2023 and 2024. |
|  |  | Mechanisms to ensure that Prevent Plan progress is regularly reviewed in CONTEST meetings. | Terms of reference reviewed and updated where appropriate |  |  |
| 1.2 Lead the risk assessment process and ensure partners are fully sighted on key risk issues | West Yorkshire Police and CBMDC Prevent. | An annual CTLP is produced that partners feed into and are consulted about.  Quarterly updates are also produced and communicated to all partners via CONTEST.  CTLP is for West Yorkshire but each area has own plan that is RAG rated. Partnership actions respond directly to current risk.  Response to changes in risk are fluent and prompt via established networks.  . | The CTLP is used to shape the District Prevent Plan and referred to throughout.  The CTLP also reflects Prevent delivery, training and projects.  Threat and risk briefings are provided to partners on a quarterly basis.  Local threat picture is referred to in all Prevent training.  Prevent self-assessment  audits are provided to partners. | Links in to all CTLP priorities to ensure that everyone is fully aware of risk. | CTLP is provided by CTU at start of 2023 and 2024.  Prevent bid for the District is submitted in January 2023 and January 2024.  Progress towards the bids  above is reported every |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Progress on these is reported at quarterly  CONTEST meetings. |  | Q at LA CONTEST. |
| 1.3 Prevent is accountable to local democratic processes – formal reports made to elected members through Corporate Overview and Scrutiny Committee | CBMDC | Transparency and accountability is supported through the existing democratic processes  Elected members understand the Prevent agenda. They also engage with it, attend Prevent related training for elected members and support Prevent related delivery in their local areas. | Attend one O/S committee per year and provide an updated report on Prevent work in the past year.  Deliver at least two members’ training sessions per year addressing relevant Prevent related topics of the moment. | Links to all CTLP priorities | O and S meeting March 2023 and March  2024.  2 delivered each year – dates to be confirmed nearer the time. |
|  |  |  | Elected members are invited to Prevent events in their areas and attend if possible. |  | Prevent events dates decided nearer the time. |
|  |  |  | Quarterly updates on Prevent work are provided for elected members. |  | Q updates are provided at same time as CONTEST  updates. |
|  |  |  | A Prevent training session is offered to all newly elected members once taking on their role. |  | After May elections. Dates decided after consultation with elected  member training department. |
| 1.4 Partnership and Safeguarding Boards are regularly updated on threat and risk and ensure Prevent safeguarding  processes are built | CBMDC- Safeguarding Adults and Children Board and Safer Communities Partnership Board | The Safeguarding Board role is integrated into Prevent delivery so that Prevents’ role in protecting vulnerable people is widely recognised as a ‘safeguarding’ function. | Agenda itemised for Prevent on partnership Boards and/or briefing provided every quarter.  Boards deliver Prevent related initiatives within their work programme | Links to all CTLP priorities | At quarterly Safeguarding Board briefings every quarter.  Prevent related sessions are offered every |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| into existing district policies and programmes |  |  | and this is updated every year.  The role of Prevent as a Safeguarding function is built into all safeguarding information. |  | safeguarding week which occurs every year at the Council. |
|  | A Prevent training session is offered to all as part of Safeguarding Week at CBMDC. |  |
|  | Representatives from Children’s and Adults Safeguarding are members of the Channel Safeguarding Panel and  attend regularly. |  |
| 1.5 Review of | CBMDC | Regular training and support for Channel | Completed training for | Links to all | Channel |
| Channel processes |  | members linked to relevant local and | members every quarter. | CTLP priorities | meetings occur |
| to ensure systems |  | national/ international risks. | An action plan is in place |  | every month, as |
| are fluent and |  | Updated Terms of Reference and review | to respond to any |  | do pre |
| support is |  | of action plan. | recommendations made |  | meetings. |
| appropriate and |  | Review of membership to ensure that | and agreed at Contest or |  | Channel training |
| effective |  | the correct people are part of the Panel. | as a response to Channel |  | is offered every |
|  |  | Ensure a Chair and Vice Chair are in | Assurance Document or |  | quarter. |
|  |  | place and of sufficient authority to | Channel audit. |  | Channel |
|  |  | ensure swift action when necessary. | Channel referrals. |  | assurance |
|  |  | Independent Channel audit process | Good representation and |  | document |
|  |  | undertaken. | attendance at Channel |  | completed by |
|  |  | Channel assurance document | meetings. |  | 12th April 2022. |
|  |  | completed for Home Office every year. | Channel referrals shared |  | Channel audit |
|  |  | 12 pre Channel meetings to ensure | in Pre Channel and with |  | will be |
|  |  | Channel meetings flow smoothly and | PEO to ensure no |  | completed by |
|  |  | everything necessary is provided. | unconscious bias. |  | April 2023 |
| 1.6 Education | CBMDC- Prevent Education | Young people recognise divisive | A dedicated Prevent | Links to all | . PEO |
| Leaders across | Officer | extreme narratives and have the | Education Officer for the | CTLP priorities, | programme of |
| Early Years, |  | knowledge and skills to build resilience | District offers help and | especially those | work is offered |
| Schools, Further |  | against hate based groups and | support to schools, | risks particularly | in PEO |
| and Higher |  | individuals. They are also aware of how | pupils, staff and parents. | targeted | newsletter every |
| education are |  | groups use contemporary issues to | This ranges from | towards the | quarter. |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| supported to deliver appropriate anti- extremism education |  | manipulate individuals and gain support via mis/dis/mal information and conspiracy theories.  Teaching and support staff recognise risks and understand reporting arrangements and their responsibilities regarding Prevent delivery and reporting.  Schools share their experience and knowledge with each other to build capacity within the education sector.  Parents and carers understand the risks in our society of young people being manipulated by groups and individuals who believe in divisive, extremist narratives. They are aware of how to get  help and support with this. | individual sessions to project work in schools.  The Education Officer creates audits, newsletters and up to date information and resources to support schools in their Prevent responsibilities.  The Education Officer continues to build the Prevent Champions network so that it has members across the district in all education sectors. | young, such as online safety, links to conspiracy theories and gaming. | At least one Prevent Champion event in 2022/23 and 2023/24.  Head Teacher and DSL network training occurs every quarter. |
|  |  |  | At least one Prevent Education Champions event is held every year to share good practise across the education sector and forge links between schools, building capacity in Prevent related education. |  |  |
|  |  |  | The PEO attends Head Teacher Partnership Groups and DSL network meetings to ensure Prevent is high on their agenda and give risk/ training updates. |  |  |
| 1.7 Prevent Champions across the Local Authority and District are  supported to embed Prevent into the | CBMDC | All areas across the LA and District that may have a link to Prevent are fully informed about risks, training and support available and referral structures. | At least one Prevent Champions event for the LA and District will be  undertaken every year and representatives will | All CTLP risks will be addressed but there may be  specific areas where the risk | At least 2 Prevent Champion  events will happen 2022- |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| work that they do across Bradford. |  |  | be in attendance from across the district.  The Prevent Champions Network will be used to share relevant Prevent information on risks, training and support. It will also be used to pass on the training via peer to peer working. | of a specific kind of radicalisation is particularly high.  E.g. Football/ sporting clubs and ERW extremism. All risks will be considered in terms of the  audience. | 24. |
|  | The Prevent Engagement Officer will share materials to help train and inform each area of current Prevent risks.  They will give advice, support and training according to need in each area and support each Prevent Champion to do  the same. |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan** | | | | | |
| **Activities** | **Lead Officer/Organisations** | **Expected Outcomes** | **Performance Measure** | **CTLP**  **Priorities** | **Completion of Actions** |
| **2. SAFEGUARDING** | | | |  |  |
| 2.1 Clear reporting/ responsibility arrangements to Adult and Children’s Safeguarding Boards | CBMDC/ West Yorkshire Police | Safeguarding boards are clear as to their role and responsibilities in Prevent delivery.  Safeguarding Boards have integrated Prevent into their core functions and programmes. | Identified in West Yorkshire Safeguarding Procedures.  Deliver Prevent sessions as part of Safeguarding Week content every year. | Links to all CTLP priorities | By end of 2022/3 and end of 2023/4 |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Adults and Children’s safeguarding has members in the Prevent Champion’s Network.  Prevent related training is delivered every year to Adult’s and Children’s  Safeguarding staff. |  |  |
| 2.2 Current generic Safeguarding packages include recognising  radicalisation and hate narratives as standard | CBMDC | Wider recognition of Prevent as a safeguarding role and where this sits alongside other safeguarding risks | Prevent safeguarding training is mandatory across LA staff training. | Links to all CTLP priorities | By end of 2022/3 and end of 2023/4 |
| 2.3 Trigger plans are in place to manage the range of circumstances in which any returnees from a conflict zone may arrive in the District, so that children can be safeguarded. | CBMDC/West Yorkshire Police | Forward planning mitigates risk and ensures children are catered for in the most sensitive and effective way.  The risk of extremism and radicalisation locally from returnees is understood, reduced  and support plans are in place | An action plan that utilises local safeguarding procedures is in place.  This is plan is ongoing and updated as required. | Links to CTLP priority regarding Syrian returnees and putting plans in place to deal with this, should it happen | Already completed. This will be amended if events should make it necessary. |
| 2.4 Support the effective and efficient delivery of the Channel support scheme. | CBMDC/ West Yorkshire Police | An effective and efficient Channel process with a broad range of partners who can meet the needs of those at risk within our district.  Support to ensure that those partners are well briefed on current risk and Prevent- related issues.  In built review of good practise. | 12 Channel safeguarding panels per year.  12 Pre Channel meetings every year to ensure that the main meetings go smoothly.  Yearly review of Channel/Prevent safeguarding processes. Recorded broad Channel membership across all sectors.  Record of review of previous good practise and a ‘lessons learned’ template for all cases leaving Channel.  Channel audit to be | Links to all CTLP priorities | Channel meetings and pre meetings completed every month.  Review of process done by March 2023 ns  2024.  Audit completed by March 2023  ‘Lesson’s learned’ every month |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | completed. |  |  |
| 2.5 Referrals to Channel are appropriate and proportional and submitted across a range of sectors | CBMDC | Greater confidence in the Channel process.  Risk is managed effectively and referrals are signposted correctly. | An increased number of referrals are heard at Channel Safeguarding Panel from a variety of areas.  Tracking of referrals shows representation across sectors.  Monthly review of referrals that don’t make Channel to ensure there is no  unconscious bias. | Links to all CTLP priorities | Monthly reviews occur every month |
| * 1. Increased support to mental health sector to recognise and respond to issue of radicalisation and hate narratives   2. Increased support to those with additional needs that may make them vulnerable to radicalisation and hate narratives. | CBMDC  CBMDC | Greater understanding and support for those with mental health issues who become vulnerable to an extremist hate narrative  A Mental Health practitioner attends Channel Panel meetings.  More knowledge, awareness and support for those working with people with mental health concerns  Greater understanding and support for those with additional needs who may be vulnerable to extremism  An additional needs practitioner attends Channel Panel meetings.  More knowledge, awareness and support for those working with people with additional needs | Increase in links with the mental health support hub for advice and support.  Deliver well attended Prevent training sessions for mental health professionals around current Prevent issues and the links to mental health.  Increased links with additional needs staff in LA.  Deliver well attended Prevent training sessions for additional needs staff around current Prevent issues and the links to additional needs. | Links to CTLP- Mental health risks  Links to CTLP- additional needs risks, particularly associated with online extremism. | Training for mental health professionals at least once every year and more as required.  Training for additional needs professionals at least once every year and more as required.  Training for DV professionals at |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2.8 Increased support for those involved in areas that crossover with radicalisation. These can include areas such as Domestic Violence. | CBMDC | Greater understanding of the links between DV and radicalisation.  A member of the DV team attends Channel Panel meetings as and when necessary.  More knowledge, awareness and support for those working in the DV team around the links  between extremism and DV. | Increased links with DV Team staff.  Deliver well attended Prevent training sessions for DV Team staff around current Prevent issues and the links to additional needs. | Links to all CTLP priorities | least once every year and more as required. |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan** | | | | | | |
| **Activities** | **Lead Officer/Organisations** | | **Expected Outcomes** | **Performance Measure** | **CTLP Priorities** | **Completion of Actions** |
| **3. ENGAGEMENT / RAISING AWARENESS** | | | | |  |  |
| 3.1 CBMDC Prevent Team to be a point of contact for support and advice to all sectors and agencies to deliver to district Prevent objectives and meet requirements of the Prevent Duty | | CBMDC | Support is available and accessible to all. All sectors know where to get support from. | ‘Prevent Champion’ network grows in membership across all sectors.  There are quarterly Prevent Champion information events concerning the latest Prevent guidance and information.  A regularly updated Prevent webpage with useful, up to date information.  Termly newsletter for schools and circulation of relevant guidance documents to all sectors.  Prevent Champions information sent out on a quarterly basis.  Elected member updated sent  out on a quarterly basis. | This will link to all CTLP priorities as it will ensure that all sectors and agencies have a point of contact to receive information and training on risk across the district. | Events every quarter for the network.  Quarterly updates for the network and elected members and termly newsletter for schools. |
| 3.2 Build engagement, | | CBMDC | Empowered | Deliver Prevent awareness | Links to all CTLP | PAG is bi annual |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| consult and raise awareness with communities on Prevent project delivery. Support and nurture community based solutions |  | communities identifying appropriate solutions that will be effective at ground level | training, relevant to communities, to every constituency in Bradford.  Wherever possible, ensure that projects used in Prevent work are grassroots, local projects.  .  Set up a Prevent Advisory Group and meet bi annually to consult around Prevent related  issues. | priorities and makes sure that all areas of the district are consulted and made aware of risk areas within the district. | Training is delivered across every constituency by the end of each year. |
| 3.3 Run a series of | CBMDC | Trust and confidence is | Five area based community | Links to all CTLP | All roundtables |
| ‘Prevent Roundtables’ |  | increased in local | roundtables per year and | priorities and | completed at end of |
| for community audiences |  | Prevent delivery | include local elected members | ensures that | each year |
| who wish to find out |  |  |  | members of the |  |
| more and contribute to |  |  |  | public are consulted |  |
| Prevent delivery |  |  |  | about future |  |
|  |  |  |  | planning. |  |
| 3.4 Develop a ‘Community Engagement Strategy’ to engage with groups  and individuals who wish for dialogue around Prevent and related subjects | CBMDC | Any concerns from communities are taken into account.  Communities understand how work to challenge extremist hate narratives is delivered. Prevent is understood better and misconceptions are minimised. | Create a Prevent Advisory Group who meet on a bi- annual basis and consult them on matters related to Prevent in our District  Create a ‘libraries roadshow’ to publicise Prevent related work across the District.  Create an OOSS Prevent Champions network and also an event to publicise within this setting. | Links to all CTLP priorities, particularly helping to raise awareness of risk amongst the local community. | Strategy completed and events all undertaken and completed every year. |
|  |  |  | Publicise the strategy on a dedicated Prevent webpage. |  |  |
|  |  |  | Strategy includes numbers of people positively engaged in Prevent. |  |  |
|  |  |  | Ensure Ward Officers are |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | consulted and fully informed  about events in different areas. |  |  |
| 3.5 Develop a network of operational Prevent leads across the District and provide a training and support programme | CBMDC/ West Yorkshire Police | More effective information and communication systems  – earlier and more effective detection of vulnerability | Annual event and training for operational Prevent leads  Health, local authority, police, education and probation represented in Prevent Champions Network, as well as community groups and third sector representatives. | Links to all CTLP priorities and provides a mechanism whereby these can be disseminated throughout the district, via Prevent Champions. | . Prevent training offered in Safeguarding week for all partners.  Prevent Champions event every year with up to date training and speakers. |
|  |  |  | Online signposting and guidance |  | Prevent Champions  Education event every year. |
|  |  |  | Create opportunities for Prevent Champions to cascade their knowledge to others in their sectors. Plan events in education, Police and health. |  | TTT for education and other partners as part of Prevent Champions  resources every year. |
| 3.6 Engage young people to educate and support challenge of extremist hate narratives | CBMDC | Young people are more resilient to hate narratives and able to challenge them.  Young people are able to cascade their knowledge and build Prevent related capacity within the education system | At least one project every year to focus on young people and any related Prevent risk.  Develop peer champions in all Prevent Champion schools.  Organise an event each year for peer champions to share good practise across the district and learn new things to disseminate at school. | Particularly focuses on CTLP risks that involve young people such as the online threat and single issues risks that are exacerbated by use of the online space, such as left wing/ anarchist viewpoints. | Prevent Champions event every year.  Peer Champions in all schools by end of 2024.  Young person’s  panel by end of 2024. |
|  |  |  | Deliver Prevent related sessions as needed, to match risk analysis according to Prevent referral data. Offer these to youth groups, sports and social groups, religious groups within the district |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Create a young person’s panel to test drive new resources/ projects and ensure they are fit  for purpose. |  |  |
| 3.7 Develop and deliver in partnership with the third sector a range of projects that meet local Prevent Objectives | CBMDC | Risks and vulnerabilities are reduced against identified threat | Independent Prevent projects delivered across sectors and across the District according to need. Need evidenced in application process. | Addresses all CTLP risk. |  |
| 3.8 Review arrangements for use of Council facilities to ensure that venues are not being used to promote hatred or extremist viewpoints | CBMDC | Prevent / Safeguarding leads are assured that proportionate arrangements are in place to prevent the organisations resources from being used to support those who to promote hatred or extremist viewpoints | Review takes place and guidance produced  Monitoring arrangements are established and operational | Addresses ALM, Far Right and Extreme Right, Left Wing/ Anarchist and single issues threats. Any groups that would use a venue to speak to an audience rather than just relying on the  online space. | Policies are currently in place. But these will be are reviewed every year and update as necessary. |
| 3.9 Update and distribute guidance to Mosques and Islamic institutions should they be contacted by a far right/ extremist group | CBMDC | Increased confidence from communities that they are being protected from extremists and that they have the most up to date guidance and  information. | Update is created, taking into account all the latest advice and information.  Distribute update to all District Islamic Institutions and Mosques | Addresses CTLP risk from Far and Extreme Right wing groups. | Update every year |
| 3.10 Ensure organisations and statutory partners hosting external speakers are aware of responsibilities to have robust equal opportunities policies which challenge hate speech, racism and homophobia | CBMDC/West Yorkshire Police | Bradford District is an increasingly difficult place for extremist speakers to deliver speeches / lectures | External speaker policy disseminated to all statutory partners.  On-line support and guidance is available and advertised for all venues in the district.  Organisations are approached if external speakers of concern are using venues and a plan is followed to offer support and  guidance. | Addresses ALM, Far Right and Extreme Right, Left Wing/ Anarchist and single issues threats. Any groups that would use a venue to speak to an audience rather than just relying on the online space. | Document is already created but is updated every year as necessary. |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 3.11 Work with those who are supporting refugees and asylum seekers so that they are aware of the risks to these communities from extremist groups and can provide help and support here necessary. | CBMDC | Make it very difficult for those wishing to exploit asylum seekers and refugees for extremist purposes. | Ensure all those who work with asylum seekers and refugees are Prevent trained and know of the help and support available and how to access it.  Ensure those who are refugees and asylum seekers have the necessary information to recognise if someone is trying to radicalise them and where to go for help  if necessary. | Addresses extremist groups who target refugees and asylum seekers to be members. Also addresses those groups who target refugees and asylum seekers as being the causes of problems. | Workers and service users given training every year |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan** | | | | | |
| **Activities** | **Lead Officer/Organisations** | **Expected Outcomes** | **Performance Measure** | **CTLP**  **Priorities** | **Completion of Actions** |
| **4. TRAINING/ COMMUNICATIONS** | | | |  |  |
| 4.1 Continue to support a network of Prevent trainers across the District to deliver quality and appropriate safeguarding training | CBMDC | Appropriate training leads to good delivery of safeguarding and education work to undermine extremist hate narratives | Prevent TTT is undertaken every quarter so that all organisations have the opportunity to have one person qualified to deliver appropriate Prevent training to staff.  Trainers are recorded and sent updates on key Prevent issues and developments. | All CTLP priorities will be addressed in the training as they will be used to inform on risk. | Training delivered every quarter. |
| 4.2 Create an updated Prevent Communications Strategy | CBMDC | Increase transparency around Prevent delivery and help build trust and  confidence in the agenda. | Strategy approved by CONTEST | All CTLP priorities addressed. | Completed but options to update every year. |
| 4.3 Updated training  programme for Prevent/CONTEST | CBMDC | Operational and  Strategic Leads understand risk and | An updated menu of rewritten  Prevent training to be circulated across the district, | All CTLP priorities  will be addressed in the training as they | .Menu and  accreditation package completed |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| groups and operational Prevent leads across the District, incorporating key current issues and risks. . |  | vulnerabilities and are equipped with knowledge/skills to make effective decisions | including online and face to face training. All relevant new issues and risks will be covered according to CTLP.  Create an updated Prevent Champions accreditation package.  An up to date spreadsheet of partners/ champions/ groups who need training and the details to ensure that this is  regularly done. | will be used to inform on risk. | by end of this year and updated for 2023/24 |
| 4.4 Training and engagement for key Council political groups | CBMDC | Local political awareness and buy-in | At least one member’s training session per year, according to need.  Training is also offered as part of the newly elected member’s training package  and roadshow. | All CTLP priorities will be addressed in the training as they will be used to inform on risk. | New member training offered post- election period each year and once a year to all elected members. |
| 4.5 Provide Prevent briefings to local authority Tier 4 Managers | CBMDC | Increased referrals to Channel from Local Authority | 2 sessions for Tier 4 Managers | All CTLP priorities will be addressed in the training as they will be used to  inform on risk. | 2 per year. |
| 4.6 Support organisations with IT equipment available to the general public to consider using filtering solutions that limit access to terrorist and  extremist material. | BMDC/West Yorkshire Police | Increased difficulty in accessing extremist material at public access points | Update and issue guidance according to most recent information. | All CTLP priorities will be addressed in the training as they will be used to inform on risk.- particularly the online risk. | Completed every year |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan** | | | | | |
| **Activities** | **Lead**  **Officer/Organisations** | **Expected**  **Outcomes** | **Performance Measure** | **CTLP**  **Priorities** | **Completion of**  **Actions** |
| **5. ON-LINE RESILIENCE** | | | |  |  |
| 5.1 Engage a range of partners to consider the nature of the on-line threat and develop a plan that tackles the key threats around online radicalisation. | CBMDC | As a district we are focusing more resource to online threat and are agile to its quickly evolving nature | Consult with partners every quarter to ensure that new and emerging threats are considered and discussed and new dangers shared.  Create an online site where help, support and resources can be stored and publicise it  amongst all our partners. | Particularly focuses on the online risk and how different groups manipulate the online space for their benefit. | Online site created by 2023/24 |
| 5.2 Education programme to explore propaganda, conspiracy theories and develop critical thinking in the district. | CBMDC and project providers | As a district, our community becomes more aware and resilient to propaganda, conspiracy theories and develops their critical thinking skills, so they are less likely to be  susceptible to online extremism. | Sessions delivered to elected members, parents,  young people and members of the community. | Particularly focuses on the online risk and how different groups manipulate the online space for their own benefit. | Plan written and updated every year. |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bradford District Prevent Plan** | | | | | |
| **Activities** | **Lead Officer/Organisations** | **Expected Outcomes** | **Performance Measure** | **CTLP**  **Priorities** | **Completion of Actions** |
| **6. Organisation** |  |  |  |  |  |
| 6.1 Map out areas in | CBMDC | Our delivery will be | Data collected from partners to | Addresses all | Consultations |
| the district to make |  | more impactful as it | help with this. Updated and | CTLP areas of risk | happen every |
| planning project work |  | targets areas of most | changed on a quarterly basis. |  | quarter |
| and training delivery |  | need. | Used to plan training and project |  |  |
| more effective |  |  | work in the future. |  |  |
| 6.2 Organise all Prevent related materials and store older materials safely | CBMDC | Materials will be easy to find and safely stored for any future use. | Materials are password protected and organised for easy access by the Prevent team. | Addresses all CTLP areas of risk. | GDPR  Administration Plan to be completed by 2024. |
|  |  |  | A review of all materials conducted and those older than 6 years of no use will be destroyed according to GDPR  rules. |  |  |